## Burndown Chart
Feature | Initial Estimate (hrs) | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Hours Left
Pi Business | 10 | 2 | 7 | 0 | 1 | 0
Pi Model | 1 | 1 | 0 | 0 | 0 | 0
Pi API | 7 | 4 | 3 | 0 | 0 | 0
Android View | 23 | 0 | 11 | 11 | 1 | 0
Android Presenter | 25 | 0 | 8 | 15 | 2 | 0
Android Model | 2 | 0 | 1 | 0 | 1 | 0
Settings | Start | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Planned Hours |  | 9 | 25 | 16 | 18
Actual Hours |  | 7 | 30 | 26 | 5
Remaining Effort | 68 | 61 | 31 | 5 | 0
Ideal Burndown | 68 | 59 | 34 | 18 | 0
| Pi Work Done | 100%
| Android Work Done | 100%
| All work done | 100%