## API
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 1 | Test designed date: | 2022-01-17
| Release Version: | 2 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-04-10
Pre-Condition | DryerAPI.py running on the Raspberry Pi.
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | REST API: Postman - Calibrate | Call Calibrate Service from API with correct security token. | 1. Open postman 2. Use correct Bearer security token 3. Post to /DryPi/calibrate |  | Dryer API calls calibrate service. Returns a AxesModel in JSON data of the range of each axis when Pi is not moving. | 200 | Dryer API calls calibrate service. Returns a AxesModel in JSON data of the range of each axis when Pi is not moving. | Pass
2 | REST API: Postman - Calibrate | Call Calibrate Service from API with incorrect security token. | 1. Open postman 2. Use correct Bearer security token 3. Post to /DryPi/calibrate |  | Dryer API does not allow access to the API | 401 | Dryer API does not allow access to the API | Pass
3 | REST API: Postman - DryerService | Call DryerService from API with correct security token | 1. Open postman 2. Use correct Bearer security token 3. Add valid Json data 4. Post to /DryPi/dryStop 5. Don't touch pi until device is finished | axisX: 0.0027 axisY: 0.0029 axisZ: 0.0040 | Dryer API calls dryer service. Returns same JSON data that was used. | 200 | Dryer API calls dryer service. Returns same JSON data that was used. | Pass
4 | REST API: Postman - DryerService | Test that the DryerAPI's can handle incorrect JSON data posted to it. | 1. Open postman 2. Use correct Bearer security token 3. Add invalid Json data 4. Post to /DryPi/dryStop | axisX: "k" axisY: 0.0029 axisZ: 0.0040 | Error Message that say invalid object | 400 | Error Message that say invalid object | Pass
5 | REST API: Postman - DryerService | Call DryerService from API with incorrect security token | 1. Open postman 2. Use incorrect Bearer security token 3. Add valid Json data 4. Post to /DryPi/dryStop 5. Don't touch pi until device is finished | axisX: 0.0027 axisY: 0.0029 axisZ: 0.0040 | Dryer API does not allow access to the API | 401 | Dryer API does not allow access to the API | Pass
6 | REST API: Postman - Adjust | Call API to adjust offset with valid data | 1. Open postman 2. Use correct Bearer security token 3. Add valid Json data 4. Post to /DryPi/adjust | adjust: 2 | Adjust data gets saved to config.txt file on the Pi. Return text that says Adjust | 200 | Adjust data gets saved to config.txt file on the Pi. Return text that says Adjust | Pass
7 | REST API: Postman - Adjust | Call API to adjust offset outside of allowed range | 1. Open postman 2. Use correct Bearer security token 3. Add Json data outside of range 4. Post to /DryPi/adjust | adjust: 7 | Return text that says data needs to be between 0 and 5 | 400 | Return text that says data needs to be between 0 and 5 | Pass
8 | REST API: Postman - Adjust | Call API to adjust offset outside of allowed range | 1. Open postman 2. Use correct Bearer security token 3. Add Json data outside of range 4. Post to /DryPi/adjust | adjust: -4 | Return text that says data needs to be between 0 and 5 | 400 | Return text that says data needs to be between 0 and 5 | Pass
9 | REST API: Postman - Adjust | Call API to adjust offset with incorrect data | 1. Open postman 2. Use correct Bearer security token 3. Add invalid Json data 4. Post to /DryPi/adjust | adjust: "k" | Error Message that say invalid object | 400 | adjust: "k" | Pass
10 | REST API: Postman - Adjust | Call API to adjust offset outside of allowed range with incorrect security token | 1. Open postman 2. Use incorrect Bearer security token 3. Add valid Json data 4. Post to /DryPi/adjust | adjust: 2 | Dryer API does not allow access to the API | 401 | adjust: 2 | Pass
11 | REST API - Postman | Washer API returns a response | 1. Open postman 2. Post to /DryPi/washerStop |  | Text that says Washer | 200 | Text that says Washer | Pass | Will also stop the Dryer Process if it is currently working.
12 | Dryer WebSocket - Postman | Washer API returns a response | 1. Open postman 2. Connect to the correct IP Address 3. Send Message with Correct Data | { "process": "Start", "axisX": 0.0027, "axisY": 0.00291, "axisZ": 0.0040 } | Returns "Dryer Finished" when the dryer stops. |  | Returns message that says if dryer has stopped. | Pass

## DryerService
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 1 | Test designed date: | 2022-01-17
| Release Version: | 2 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-04-10
Pre-Condition | Don't run this from the API, but the file directly
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | DryerService - Calibrate | Test that the program works if calibrated properly | 1. Run the program 2. Wait until the console says the calibration is done. 3. For two sets, move the pi a little bit. 4. Don't touch it until it ends. |  | The device will correctly determine the device has moved when it does and not when it hasn't. |  | The device correctly determined the device did move when it did and not when it did not. | Pass | Manually run this process by calling the calibrate and checking method one after another. Ex: justMain(calibrate())
2 | DryerService - Calibrate | Test that the program doesn't work if not calibrated properly by moving the device a lot | 1. Run the program 2. Move the device at least an inch while calibrating. 3. For two sets, move the pi less then an inch when detecting motion. 4. Don't touch it until it ends. |  | The device will incorrectly determine that the device is not moving, when it has. |  | The device incorrectly determined the device did not move when it did. | Pass | Manually run this process by calling the calibrate and checking method one after another. Ex: justMain(calibrate())
3 | DryerService - Calibrate | Test that the program doesn't work if not calibrated properly by moving the device a little | 1. Run the program 2. Move the device slightly while calibrating. 3. For two sets, move the pi slightly when detecting motion. 4. Don't touch it until it ends. |  | The device will incorrectly determine that the device is not moving, when it has. |  | The device incorrectly determined the device did not move when it did. | Pass | Manually run this process by calling the calibrate and checking method one after another. Ex: justMain(calibrate())
4 | DryerService - False Positive | Test that the program will only end after the device detects no movement, twice in a row. | 1. Run the program 2. Use valid data 3. Three times, move the device for one set, then do not move it for the other. 4. Don't touch it until it ends. | axisX: 0.0027 axisY: 0.0029 axisZ: 0.0040 | The device will only stop after the 7th set, where it has not moved twice in a row. |  | The Device stopped after the 7th set, when there was no movement two times in a row. | Pass | Manually run this process by using the test data in the just main method
5 | DryerService | Test that the program will end quickly if no movement is detected. | 1. Run the program 2. Use valid data 3. Don't touch the Pi for the two set. 4. Wait until it finishes. | axisX: 0.0027 axisY: 0.0029 axisZ: 0.0040 | The device will stop after two sets. |  | The device stopped after 2 sets. | Pass | Manually run this process by using the test data in the just main method

## Navi App
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 2 | Test designed date: | 2022-01-31
| Release Version: | 2 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-04-10
Pre-Condition | Open the application on Galaxy S8+ and start on the Home Page.
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Navigation - Dryer | Test the user can go to the Dryer page and back to Home | 1. Click Dryer Button 2. Click Back Button |  | The application will go to the dryer page then back to the Home Page. |  | The application will go to the dryer page then back to the Home Page. | Pass
2 | Navigation - Calibrate | Test the user can go to the Calibration page and back to Home | 1. Click Settings Button 2. Click Calibration Button 3. Click Back Twice |  | The application will go to the Settings page then to the Calibrate Page. Then back to the Settings page, then the Home Page |  | The application will go to the Settings page then to the Calibrate Page. Then back to the Settings page, then the Home Page | Pass
3 | Navigation - Adjust | Test the user can go to the Adjust page and back to Home | 1. Click Settings Button 2. Click Adjust Button 3. Click Back Twice |  | The application will go to the Settings page then to the Adjust Page. Then back to the Settings page, then the Home Page |  | The application will go to the Settings page then to the Adjust Page. Then back to the Settings page, then the Home Page | Pass
4 | Navigation - Notify | Test the user can go to the Notify page and back to Home | 1. Click Settings Button 2. Click Notify Button 3. Click Back Twice |  | The application will go to the Settings page then to the Notify Page. Then back to the Settings page, then the Home Page |  | The application will go to the Settings page then to the Notify Page. Then back to the Settings page, then the Home Page | Pass
5 | Navigation - Settings | Test the user can go to the Settings page and back to Home | 1. Click Settings Button 2. Click Back Button |  | The application will go to the Settings page then back to the Home Page. |  | The application will go to the Settings page then back to the Home Page. | Pass

## Calibrate App
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 3 | Test designed date: | 2022-02-20
| Release Version: | 3 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-04-10
Pre-Condition | Open the application on Galaxy S8+ and start on the Calibrate Page. Assume DryerAPI is running on Pi unless stated otherwise.
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Calibrate - Success | Test that Calibrate works on the phone | 1. Press the Calibrate Button 2. Wait until the Buttons are green 3. Check that data on Pi Console and Android Console are the same. |  | Pi will respond. Receive SavedRange data and write to a text file. Buttons should be yellow when in progress and green when successfully finished. |  | Pi respond. Received SavedRange data and wrote to a text file. Buttons are yellow when in progress and green when successfully finished. | Pass
2 | Calibrate - Fail | Test Calibrate does not work if API is not running. | 1. Make sure DryerAPI is off and not running in the background. 2. Press the Calibrate Button 3. Wait until Text Changes |  | Text will inform the user the calibration failed and the buttons should change to Red after a minute. Console will show Connect Exception. |  | Text informed the user the calibration failed and the buttons changed to Red after a minute. Console showed Connect Exception. | Pass
3 | Calibrate - Fix | After a failure, test that the device can Successfully calibrate without restarting the app. | 1. Run Test 2, Calibrate - Fail 2. Turn on Dryer API. 3. Press the Calibrate Button 4. Wait until the Buttons are green 5. Check that data on Pi Console and Android Console are the same. |  | Pi will respond. Receive SavedRange data and write to a text file. Buttons should be yellow when in progress and green when successfully finished. |  | Pi respond. Received SavedRange data and wrote to a text file. Buttons are yellow when in progress and green when successfully finished. | Pass
4 | Calibrate - Buttons Turned off | Test that the buttons cannot be used while Calibration is in progress. | 1. Push the Calibrate Button 2. Attempt to push the Calibrate Button again 3. Attempt to Push the Back Button |  | The phone application will prevent the user from clicking either button. |  | The phone prevented the user from pressing the Calibrate or Back button. | Pass

## Adjust App
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 3 | Test designed date: | 2022-02-20
| Release Version: | 3 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-04-10
Pre-Condition | Open the application on Galaxy S8+ and start on the Adjust Page. Assume DryerAPI is running on Pi unless stated otherwise.
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Adjust - Success | Test that adjust works on the phone | 1. Move the Seekbar to where the Text says 'Not Sensitive'. 2. Press Confirm Button. 3. Wait for Button to Turn Green 4. Move the Seekbar to where the Text says 'Below Average Sensitivity'. 5. Press Confirm Button. 6. Wait for Button To Turn Green 7. Move the Seekbar to where the Text says 'Average Sensitivity'. 8. Press Confirm Button. 9. Wait for Button to Turn Green 10. Move the Seekbar to where the Text says 'Above Average Sensitivity'. 11. Press Confirm Button. 12. Wait for Button to Turn Green 13. Move the Seekbar to where the Text says 'Extremely Sensitive'. 14. Press Confirm Button. 15. Wait for Button to Turn Green |  | The Pi's API should respond each time the user clicks Confirm. Each Sensitivity should be responded with a number. Not Sensitive = 1, Below Average Sensitivity = 2, Average Sensitivity = 3, Above Average Sensitivity = 4, Extremely Sensitive = 5 |  | The Pi's API responded each time Confirm was clicked. Each Sensitivity responded with a number. Not Sensitive = 1, Below Average Sensitivity = 2, Average Sensitivity = 3, Above Average Sensitivity = 4, Extremely Sensitive = 5 | Pass
2 | Adjust - Fail | Test adjust does not work if API is not running. | 1. Make sure DryerAPI is off and not running in the background. 2. Press the Confirm Button 3. Wait until the Buttons change to red. |  | Text will inform the user the Adjust failed and the buttons should change to Red after a minute. Console will show Connect Exception. |  | Text informed user it failed. Changed to red. Connect Exception shown. | Pass
3 | Adjust - Fix | After a failure, test that the device can Successfully adjust without restarting the app. | 1. Run Test 2, Adjust - Fail 2. Turn on Dryer API. 3. Press the Confirm Button at any adjustment level 4. Wait until the Buttons are green 5. Check the Pi Console |  | Pi will respond. The Adjustment level should match the number. (Check Expected result in Test 1). |  | Pi responded. Adjustment level matched expected result. | Pass
4 | Adjust - Buttons Turned off | Test that the buttons cannot be used while Adjust is in progress. | 1. Make sure the Dryer API is not running. 2. Push the Confirm Button at any level 3.. Attempt to push the Confirm Button again 4. Attempt to Push the Back Button |  | The phone application will prevent the user from clicking either button. |  | The phone prevented the confirm or back button from being pressed. | Pass | The time to attempt this goes by quickly.

## Notify App
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 3 | Test designed date: | 2022-03-06
| Release Version: | 3 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-04-10
Pre-Condition | Open the application on Galaxy S8+ and start on the Notify Page. Assume DryerAPI is running on Pi unless stated otherwise. Dryer Page needs to be functional.
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Notify - Success | Test that Notify works on the phone | 1. Tap the Spinner and pick "Never" 2. Press Confirm Button. 3. Wait for Button to Turn Green 4. Tap the Spinner and pick "1 Minute" 5. Press Confirm Button. 6. Wait for Button To Turn Green 7. Tap the Spinner and pick "5 Minutes" 8. Press Confirm Button. 9. Wait for Button to Turn Green 10. Tap the Spinner and pick "10 Minutes" 11. Press Confirm Button. 12. Wait for Button to Turn Green 13. Tap the Spinner and pick "15 Minutes" 14. Press Confirm Button. 15. Wait for Button to Turn Green |  | LogCat will repeat the String before it is saved to the text file. So in order one should see "Never", "1 Minute", "5 Minutes", "10 Minutes", and "15 Minutes" |  | LogCat will repeated the String before it was saved to a text file. So in order "Never", "1 Minute", "5 Minutes", "10 Minutes", and "15 Minutes" | Pass
2 | Notify Worker - One Notification | Test not getting an extra notification if 'Never' is picked | 1. Tap the Spinner and pick "Never" 2. Press Confirm Button. 3. Wait for Button to Turn Green 4. Go Back twice, then go to Dryer 5. Select Start and wait until Dryer Detection ends 6. After the first Notification wait 15 Minutes. |  | Only one Notification should be sent after the Dryer Worker stops. |  | Only one Notification was sent after the Dryer Worker stopped. | Pass
3 | Notify Worker - Reoccurring Notifications | Test getting a reoccurring notifications after the first one is sent. | 1. Tap the Spinner and pick "1 Minute" or "5 Minutes" 2. Press Confirm Button. 3. Wait for Button to Turn Green 4. Go Back twice, then go to Dryer 5. Select Start and wait until Dryer Detection ends 6. After the first Notification wait 1 or 5 Minutes for a second one. 7. Wait another 1 or 5 minutes for a third. |  | A second and third notification should be sent after the first. |  | A second and third notification was sent after the first. | Pass
4 | Notify Worker - Reoccurring Long Notifications | Test getting a reoccurring notifications after a longer period once the first one is sent. | 1. Tap the Spinner and pick "10 Minute" or "15 Minutes" 2. Press Confirm Button. 3. Wait for Button to Turn Green 4. Go Back twice, then go to Dryer 5. Select Start and wait until Dryer Detection ends 6. After the first Notification wait 10 or 15 Minutes for a second one. 7. Wait another 10 or 15 minutes for a third. |  | A second and third notification should be sent after the first. |  | A second and third notification was sent after the first. | Pass

## Dryer App
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 3 | Test designed date: | 2022-03-06
| Release Version: | 3 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-03-07
Pre-Condition | Open the application on Galaxy S8+ and start on the Dryer Page. Assume DryerAPI is running on Pi unless stated otherwise.
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Dryer - Success | Test that Dryer Reminder Works. | 1. Press the Start Button 2. Move the Pi for a few seconds. 3. After 30 to 45 seconds a notification should be sent and the buttons should change to green. |  | After the Pi stops detecting movement the user should get a notification that their dryer has stopped. |  | After the Pi stopped detecting movement a notification that their dryer has stopped was sent. | Pass
2 | Dryer - Success Long | Test that Dryer Reminder Works after more then 10 Minutes. | 1. Press the Start Button 2. Move the Pi for longer then 10 minutes 3. Wait until buttons turn green. |  | After the Pi stops detecting movement the user should get a notification that their dryer has stopped, even after 10 minutes. |  | After the Pi stopped detecting movement a notification that their dryer has stopped was sent, even after 10 minutes. | Pass
3 | Dryer - Fail | Test Dryer does not work if API is not running. | 1. Make sure DryerAPI is off and not running in the background. 2. Press the Start Button 3. Wait until Text Changes |  | Text will inform the user the Dryer Reminder failed and the buttons should change to Red after a minute. Logger should show an error. |  | Text inform the user the Dryer Reminder failed and the buttons changed to Red after a minute. Logger should show an error. | Pass
4 | Dryer - Fix | After a failure, test that the device can Successfully work without restarting the app. | 1. Run Test 2, Dryer - Fail 2. Turn on Dryer API. 3. Press the Start Button 4. Wait until the Buttons are green and a notification is sent. |  | After the Pi stops detecting movement the user should get a notification that their dryer has stopped. |  | After the Pi stops detecting movement the user got a notification that their dryer stopped. | Pass
5 | Dryer - Stop Reoccurring Notifications | Test that the recurring Notification stop after pressing the button. | 1. Make Sure Notification Settings are not on 'Never'. 2. Press the Start Button 3. After 30 to 45 seconds a notification should be sent and the buttons should change to green. 4. Wait until a second notification is sent. 5. Press "I got my Laundry" 6. Wait for another notification. |  | The Phone sends one notification after the dryer stops and another recuring notification saying not to forget about the laundry. After the button is press, no More notifications are sent. |  | The Phone sent one notification after the dryer stopped and another recuring notification saying not to forget about the laundry. After the button was pressed again, no more notifications were sent. | Pass
6 | Dryer - End Early | After Starting the Dryer Detection, press the same button to turn off Dryer and Notify Worker. | 1. Make Sure Notification Settings are not on 'Never'. 2. Press the Start Button 3. Immediately Press, "I got my Landry" 4. Wait for 3 Minutes |  | The Phone will say the dryer stopped and the user should not get any notifications. |  | The Phone said the dryer stopped and no notifications were sent. | Pass
7 | Dryer - Back Button Turned off | Test that the Back button cannot be used while Dryer is in progress. | 1. Push the Calibrate Button 2. Attempt to push the Calibrate Button again 3. Attempt to Push the Back Button |  | The phone application will prevent the user from clicking either button. |  | After application starts, back button cannot be pressed. | Pass

## Start App
Your Company LOGO | Project Name: | Dryer Reminder | Test designed by: | Michael Mohler
| Module Name: | 3 | Test designed date: | 2022-04-05
| Release Version: | 3 | Test executed by: | Michael Mohler
|  |  | Test execution date: | 2022-03-07
Pre-Condition | Open the application on an Android Emulator with wiped data. Assume you are at the start page. This will be used to test when the user first uses the app.
Dependencies:
Test Priority
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-Condition | Actual Result | Status | Notes
1 | Start - No Calibration Found | Test that the user will be taken to the Calibrate Page if no data is detected. | 1. Press the Dryer Button 2. Check to make sure user is taken to Calibrate page. 3. Calibrate the Device. |  | The user will go to the Calibrate page and they should be able to succesfully calibrate the device. |  |  | Pass
2 | Start - Calibration Found | Test the user will be taken to the Dryer Page if their device was calibrated. | 1. Press the Dryer Button 2. Check the User is on the Dryer Page. |  | The user should be on the Dryer Page. |  |  | Pass
3 | Start - No Reminder Found | Test that the Dryer Page will not send a reminder notification if no data is found. | 1. Press the Dryer Button to go to the Dryer Page 2. Press Dryer Button and wait for the Device to send a notification. 3. Wait for 15 Minutes for a reminder notification. |  | The user should not get another noticiation after the first one is ent. |  |  | Pass
4 | Start - Reminder Found | Test that the Dryer Page will send a reminder notification if data is found and settings are not "Never" | 1. Go to Settings and then Notification. 2. Save reminder to something other then "Never". 3. Go Back to Home Page. 4. Press the Dryer Button to go to the Dryer Page 5. Press Dryer Button and wait for the Device to send a notification. 6. Wait for 15 Minutes for a reminder notification. |  | The phone should send a reminder notification, in the time selected, after the first. |  |  | Pass